## WBS
ID | Work | Requirement | Est | Imp | Note | Issue ID
1 | 产品库首页
1.1 | 广告活动区 | 作为用户，可以查看最新的推广活动
1.1.1 | 实现广告查询接口
1.1.2 | 实现广告Model/Presenter
1.1.3 | 实现广告View
1.1.4 | 实现广告Control
1.2 | 特色分类区 | 作为用户，可以按名人推荐或美容大奖分类查询商品
1.2.1 | 实现特色分类查询接口
1.2.2 | 实现特色分类Model/Presenter
1.2.3 | 实现特色分类View
1.2.4 | 实现特色分类Control
1.3 | 快速搜索区 | 作为用户，可以用关键词在产品/品牌/功效三个范围内进行搜索
1.3.1 | 实现快速搜索查询接口
1.3.2 | 实现快速搜索Model/Presenter
1.3.3 | 实现快速搜索View
1.3.4 | 实现快速搜索Control
1.4 | 热门小样展示区 | 作为用户，可以查看热门兑换小样
1.5 | 分类区 | 作为用户，可以按分类查询商品
2 | 产品查询列表页面
2.1 | 工具栏区
2.2 | 筛选列表区
2.3 | 产品列表区
3 | 产品页面
3.1 | 工具栏
3.2 | 图片展示区 | 作为用户，可以查看各个SKU的图片以及兑换价格
3.3 | 操作区（点评等） | 作为用户，可以收藏，点评以及为该商品写心得
3.4 | 导购区 | 作为用户，可以查看主要平台的售价
3.5 | 价格区 | 作为用户，可以查看各地零售价格
3.6 | 推荐区 | 作为用户，可以看到该商品哪些名人推荐过，以及获得哪些大奖
3.7 | 商品详情区
3.8 | 统计区 | 作为用户，可以查看该商品的统计信息
3.9 | 点评区 | 作为用户，可以查看商品的点评详情
4 | 商品详情页面 | 作为用户，可以查看商品的详情

## Sprint-Template
Sprint 1 - Melish
Team: Melish D， H， Y，W
| Daily Scrum Meeting: 10:00 - 10:15 |  |  |  |  | Days Left in Sprint: |  | -42199 |  | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
| Start Date: |  |  |  | 2014-10-06 |  |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [5 empty] | Sprint
[6 empty] | 24.10. |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
| End Date: |  |  |  | 2014-10-26 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Review
| !! Do not edit or delete this row !! |  | =IF(ACC!B2>0,ACC!B2," ") | 0 |  | Not Started
| !! Do not edit or delete this row !! |  | =IF(ACC!B3>0,ACC!B3," ") | 1 |  | In Progress
| !! Do not edit or delete this row !! |  | =IF(ACC!B4>0,ACC!B4," ") | 2 |  | Completed
| !! Do not edit or delete this row !! |  | =IF(ACC!B5>0,ACC!B5," ") |  |  | Shifted
| !! Do not edit or delete this row !! |  | =IF(ACC!B6>0,ACC!B6," ") |  |  | Cancelled
| !! Do not edit or delete this row !! |  | =IF(ACC!B7>0,ACC!B7," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B8>0,ACC!B8," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B9>0,ACC!B9," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B10>0,ACC!B10," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B11>0,ACC!B11," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B12>0,ACC!B12," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B13>0,ACC!B13," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B14>0,ACC!B14," ")
| !! Do not edit or delete this row !! |  | #=IF(ACC!B15>0,ACC!B15," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B16>0,ACC!B16," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B17>0,ACC!B17," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B18>0,ACC!B18," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B19>0,ACC!B19," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B20>0,ACC!B20," ")
| !! Do not edit or delete this row !! |  | =IF(ACC!B21>0,ACC!B21," ")
# | Major Deliverable | ReqKey | ACC | Team ID | Owner | Status | PBL hours | Used hours | Sum hours | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10 | 2014-10-11 | 2014-10-12 | 2014-10-13 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-17 | 2014-10-18 | 2014-10-19 | 2014-10-20 | 2014-10-21 | 2014-10-22 | 2014-10-23 | 2014-10-24 | 2014-10-25 | 2014-10-26
| Calculated hours | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Availability | [5 empty] | 0 | 0 | 208 | 8 | 8 | 8 | 8 | 8 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 16 | 16 | 8 | 8 | 8 | 8 | 16 | 16 | 0
0 | Availability overview | [8 empty] | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
| D | [7 empty] | 52 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 4 | 4
| H | [7 empty] | 52 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 4 | 4
| Y | [7 empty] | 52 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 4 | 4
| W | [7 empty] | 52 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 4 | 4
0 | Planned Tasks | [8 empty] | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
1 | 产品库页面
1.1 | 定义产品库页面需求
1.2 | 创建产品库数据库
1.3 | 创建产品库UI
Note on K5: Keeps day empty on the right of current day for automatic trend line
Note on K6: Calucaltes linear line
Note on E32: 作者: 0 - Beide Teams 1 - Team 1 2- Team 2
Note on G32: - Not Started - In Progress - Completed - Shifted
Note on H32: Initial Estimates from Productbacklog in hours
Note on I32: Akkumulierten Aufwand hier eintragen
Note on J32: Feinschaetzung hier eintragen